## Week 1
Time Table Date : 22 - 26 April
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday |  | Total / week
| 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28
Mihael Druzeta | [16 empty] | Total Hours = 8 weeks
[16 empty] | Mihael Druzeta | 209
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week | Mihaela Covali | 201.15
| Team Meeting | 3 | Idea discussion | 3 | Idea discussion | 2 | Finishing touches | 4 | Idea discussion | 4 |  |  |  |  | 27.5 | Timofei Arefev | 180
| Code of conduct | 0.5 | Process | 3 | Teacher meeting | 0.5 | Writing documentation | 1 | Process | 3 | [5 empty] | Daryl Genove | 186.5
[5 empty] | Organising Team Work | 1 | Teacher meeting | 0.5 | [7 empty] | Peter Zlamala | 51.5
[5 empty] | Logo design | 2 | [9 empty] | Erika Nicolau | 196
[16 empty] | Jia Men Lam | 180.5
Total |  | 3.5 |  | 6 |  | 5.5 |  | 5.5 |  | 7 |  | 0 |  | 0
Mihaela Covali
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Code Of Coduct | 0.5 | Brainstorming Ideas | 4 | Clasifying Ideas | 2 | Quality Control | 4 | Design Documentation | 4 | Quality Control | 4 |  |  | 28.5
| Brainstorming Ideas | 3 |  |  | Teachers Meeting | 0.25
[5 empty] | Organising Team Work | 0.25
[5 empty] | Design Documentation | 5
[5 empty] | Logo Design | 0.5
[5 empty] | Discussing Needed Components | 1
Total |  | 3.5 |  | 4 |  | 9 |  | 4 |  | 4 |  | 4 |  | 0
Timofei Arefev
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Idea generation for project | 3 | Idea generation for project | 3 | Work on documentation | 5 | Make app design | 3 | Work on documenta | 4 |  |  |  |  | 18
Total |  | 3 |  | 3 |  | 5 |  | 3 |  | 4 |  | 0 |  | 0
Daryl Genove
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Team Meeting | 3 | Team Meeting | 3 | Team Meeting | 3 | Functional Requirement | 3 | Team Meeting | 3 | Presentation(Poll) | 2.25 | Checking Quality (Presentation) | 3 | 27.7
[7 empty] | Priority Level | 2 | Team Meeting | 3 |  |  | Checking Collaborative Goal | 0.45
[9 empty] | Risk Analysis | 2
Total |  | 3 |  | 3 |  | 3 |  | 5 |  | 8 |  | 2.25 |  | 3.45
Peter Zlamala
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Code of conduct | 0.5 | team meeting | 3 | team meeting | 3 | budget creationand alocating components | 3 | team meeting | 3 | finishing budget and documents | 2 | deadline for poll and division of work | 2 | 19
| Project discusion | 2.5
Total |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 2 |  | 2
Erika Nicolau
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Code Of Coduct | 0.5 | Brainstorming Ideas(online) | 3 | Choosing idea as main topic | 2 | Research about the project | 4 | Design Documentation | 4 | Design Documentation - Creating one final document | 2 | Design Documentation - Quality control | 2 | 23.5
| Brainstorming Ideas(online) | 3 |  |  | Logo decisions | 1
[5 empty] | Implementation next actions | 2
Total |  | 3.5 |  | 3 |  | 5 |  | 4 |  | 4 |  | 2 |  | 2
Jia Men Lam
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Meeting with new groep - code of conduct - role position | 4 | Brainstorming Ideas in atelier | 3 | Choosing idea as main topic - logo decisions - implementation decisions | 5 | Requirement analysis: - Nonfunctional design - priority levels | 2.5 | Requirement analysis - quality control | 2 | Requirement analysis - quality control | 1 |  |  | 22.5
|  |  | Researching more information for new ideas | 1 |  |  |  |  | Meeting / atelier | 3
|  |  | Create the time table | 1
Total |  | 4 |  | 5 |  | 5 |  | 2.5 |  | 5 |  | 1 |  | 0

## Week 2
Time Table Date : 6 - 10 Mei
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday |  | Total / week
| 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12
Mihael Druzeta
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Writing documents | 2 | Writing documents | 2 | Team discussion | 2 | Learning React Native | 2 | Learning React Native | 5 | Learning React Native | 3 | Learning React Native | 3 | 36
| Working on presentation | 2 | Working on Presentation | 3 | Teacher meeting | 0.5 | [6 empty] | Creating repository | 3
| Process | 3 | Creating collab. goal | 1 | Rework document | 1.5
|  |  | Getting feedback | 0.5 | Rework collab. goal | 1.5
[5 empty] | Final Adjustments | 1
Total |  | 7 |  | 6.5 |  | 6.5 |  | 2 |  | 5 |  | 3 |  | 6
Mihaela Covali
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Team Feedback on Design Documenatation | 0.5 | Writing Common Goal | 3 | Working on Presentation | 2 | Learning React Native | 2 | Learning React Native | 2.5 | Learning React Native | 1 | Learning React Native | 1 | 23.5
| Organising Work for Presentation | 0.5 | Team Feedback Presentation | 0.5 | Teachers Meeting | 0.5
| Presentation Design | 1 | Working on Presentation | 3 | Final Adjustments on Design Documentation | 3
| Presesntation Plan Organisation | 1 |  |  | Choosing Coding Enviroment | 0.5
[5 empty] | Assigning Group Work | 1.5
Total |  | 3 |  | 6.5 |  | 7.5 |  | 2 |  | 2.5 |  | 1 |  | 1
Timofei Arefev
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Work o presentation | 3 | Prepare for the presentation | 3 | Presentaion | 1 | Learning React Native | 3 | Learning React Native | 3 | Learning React Native | 3 |  |  | 19
[5 empty] | Fix documentation | 2
[5 empty] | Participationg in meeting | 1
Total |  | 3 |  | 3 |  | 4 |  | 3 |  | 3 |  | 3 |  | 0
Daryl Genove
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Team Meeting | 3 | Team Meeting | 3 | Team Meeting | 3 | Learning React Native | 2 | Learning React Native | 2 | Learning React Native | 1,5 | Learning React Native | 3 | 19
| Time Table | 3
Total |  | 6 |  | 3 |  | 3 |  | 2 |  | 2 |  | 0 |  | 3
Peter Zlamala
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Prepare the presentation | 3 | fixing agenda | 0.5 | team communicationand | 1 | Learning React Native | 2 | Learning React Native | 4 | Learning React Native | 3 |  |  | 18.5
[5 empty] | catching up | 2 |  |  |  |  | learning python | 3
Total |  | 3 |  | 0.5 |  | 3 |  | 2 |  | 4 |  | 6 |  | 0
Erika Nicolau
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Process | 0.5 | Team meeting | 2 | Preparing for the initial poll | 1.5 | Research about the project | 3 | Reasearch about the components | 3 | Learning about NFC reader | 2 |  |  | 25.5
| Team Meeting | 2.5 | Writing the common goals | 2 | Initial Poll | 0.5 | Learning about Raspberry Pi | 2
| Working on presentation | 2 | Revising the presentation | 2 | Making the adjustments of the documents | 2
[5 empty] | Filling in the time table | 0.5
Total |  | 5 |  | 6 |  | 4.5 |  | 5 |  | 3 |  | 2 |  | 0
Jia Men Lam
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Discussion about presentation | 0.5 | Group Collabolarion disccussion for profesional skills | 2 | Meeting / general | 3 |  |  | Reactive Native - Self study | 5 | Reactive Native - Self study | 3 |  |  | 20
| Documents in general: - quality control | 0.5 | Presentation discussion | 1 | Meeting with Teachers | 0.5
| Meeting | 3 |  |  | Meeting : document corrections | 1.5
Total |  | 4 |  | 3 |  | 5 |  | 0 |  | 5 |  | 3 |  | 0

## Week 3
Time Table Date : 13 - 17 Mei
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday |  | Total / week
| 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
Mihael Druzeta
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Writing documents | 1 | Atelier | 3 | Atelier | 3 | Writing documents | 1 | Atelier | 3 |  |  |  |  | 22
| Learning React Native | 2 | Learning React Native | 2 | Process | 3 |  |  | Process | 3
[5 empty] | Writing documents | 1
Total |  | 3 |  | 5 |  | 7 |  | 1 |  | 6 |  | 0 |  | 0
Mihaela Covali
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Setting up React enviroment | 2 | Working on the app | 2 | Quality control the code | 2 | Learning React Native | 3 | Learning React Native | 3 | Technical resesarch for the project | 1 | Technical Research for the project | 1.5 | 25.5
| Learning React | 3 | Learning React Native | 1 | Learning React Native | 3
| Working on the bag app | 4
Total |  | 9 |  | 3 |  | 5 |  | 3 |  | 3 |  | 1 |  | 1.5
Timofei Arefev
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Setting up React enviroment for project | 2 | Helping team members | 2 | Helping team members | 2 | Learning React Native | 3 | Learning React Native | 3 |  |  |  |  | 21
| Learning React | 2 | Learning React Native | 1 | Learning React Native | 2
| Working on the bag app | 4
Total |  | 8 |  | 3 |  | 4 |  | 3 |  | 3 |  | 0 |  | 0
Daryl Genove
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| team meeting | 3 | team meeting | 3 | team meeting | 3 | Coding(Light and Dark Mode) | 3 | team meeting | 3 |  |  |  |  | 19.65
| Starting Page (Project App) | 1 | Starting Page Animation (Project App) | 1.5 | Research (Light and Dark Mode) | 2 |  |  | Upload Files(Github) | 0.15
Total |  | 4 |  | 4.5 |  | 5 |  | 3 |  | 3.15 |  | 0 |  | 0
Peter Zlamala
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| team meeting | 3 | self study python | 3 | team meeting | 3 | self study Python | 3 | [6 empty] | 14
|  |  | python library research | 1 | react native study | 1
Total |  | 3 |  | 4 |  | 4 |  | 3 |  | 0 |  | 0 |  | 0
Erika Nicolau
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Setting the React Native environment | 1 | Learning React Native | 4 | Learning React Native | 3 | Developing the main page of the page | 5 | Merging the switch from light mode to dark mode to my code | 4 |  |  |  |  | 25.5
| Resolving techincal problems for React | 3 | Starting a test project in Recat Native | 2 | Developing the main page of the page | 2 |  |  | Uploading the main page on git | 1
[9 empty] | Filling in the time table | 0.5
Total |  | 4 |  | 6 |  | 5 |  | 5 |  | 5.5 |  | 0 |  | 0
Jia Men Lam
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Reactive Native - Self study | 4 | Reactive Native - Self study | 4 | Reactive Native - Self study - Working on user interface | 5 | Reactive Native - Self study - Working on user interface | 3 | Reactive Native - Self study - Working on user interface - learning how to use xcode | 5 | learning how to use xcode | 2 |  |  | 23
Total |  | 4 |  | 4 |  | 5 |  | 3 |  | 5 |  | 2 |  | 0

## Week 4
Time Table Date : 20 - 24 Mei
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday |  | Total / week
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26
Mihael Druzeta
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Studying | 2 | Atelier | 3 | Atelier | 3 | Career Day | 8 | Atelier | 3 |  |  |  |  | 30
|  |  | Writing documents | 2 | Process | 3 |  |  | Writing documentation | 1
[9 empty] | Coding the app | 2
[9 empty] | Process | 3
Total |  | 2 |  | 5 |  | 6 |  | 8 |  | 9 |  | 0 |  | 0
Mihaela Covali
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Quality Control Teams' Work | 1 | Learning React Native | 1.5 | Learning React | 2 | Companies Meeting | 8 | Working on the app | 3 |  |  |  |  | 27
| Updating documentation | 3 | Learning Python | 2.5 | Learning Python | 3 |  |  | Starting setting up Raspberry Pi | 3
Total |  | 4 |  | 4 |  | 5 |  | 8 |  | 6 |  | 0 |  | 0
Timofei Arefev
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
|  |  | Organizing the project activity | 2 | Help people with the app | 3 | Career Day | 8 | Align team goals acording to changes in the plan | 3 | preperation for setting up thr raspberry pi | 3 | preperation for setting up thr raspberry pi | 3 | 23
|  |  | Working on app | 1
Total |  | 0 |  | 3 |  | 3 |  | 8 |  | 3 |  | 3 |  | 3
Daryl Genove
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Holiday |  | React native (Self-Study) | 3 | Team Collaboration | 3 | Career Day | 8 | Team Collaboration | 3 | 360 Degree Feedback | 1.5 |  |  | 31.5
|  |  | Research (How the project works) | 5 | Atelier | 3 |  |  | Application Design (Refix) | 3
[5 empty] | 360 Degree Feedback | 2
Total |  | 0 |  | 8 |  | 8 |  | 8 |  | 6 |  | 1.5 |  | 0
Peter Zlamala
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
0
Total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Erika Nicolau
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Studying python | 3 | Studying python | 2 | Studying python | 3 | Career Day | 8 | Set up the Raspberry Pi | 4 |  |  |  |  | 25
|  |  | Writing documents | 2 |  |  |  |  | Updating the time table | 1
[9 empty] | Quality control | 2
Total |  | 3 |  | 4 |  | 3 |  | 8 |  | 7 |  | 0 |  | 0
Jia Men Lam
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Reactive Native - Self study - Working on user interface | 2 | Reactive Native - Self study - Working on user interface - working bag interface - working items interface | 3 | Reactive Native - Self study - Working on user interface - working bag interface - working items interface - working on add - remove - rename bags | 5 | Reactive Native - Self study - Working on user interface - working bag interface - working items interface - working on add - remove - rename items | 4 | Reactive Native - Self study - Working on user interface - working bag interface - working items interface - working on add - remove - rename items | 5 |  |  |  |  | 23
| Learning basics - bluetooth connections - wifi connections | 4 | sick |  | sick |  | sick
Total |  | 6 |  | 3 |  | 5 |  | 4 |  | 5 |  | 0 |  | 0

## Week 5
Time Table Date : 27 - 31 Mei
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday |  | Total / week
| 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 1 |  | 2
Mihael Druzeta
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Developing app | 3 | Developing app | 3 | Atelier | 3 | Atelier | 3 | Atelier | 3 |  |  |  |  | 25
| Atelier | 3 | Atelier | 3 | Developing the bag | 1
|  |  | Process | 3
Total |  | 6 |  | 9 |  | 4 |  | 3 |  | 3 |  | 0 |  | 0
Mihaela Covali
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Setting Raspberry Pi and confronting technical diffictulties | 3 | Setting Raspberry Pi and confronting technical difficulties | 3 | Setting up the NFC tags | 1 | Research to connect the speaker to the Raspberry Pi | 4 | Control teams' progress | 1 | Research for the project | 2 | Research for the project | 2 | 30.15
| Project Research | 2.5 | Project Research | 2 | Controll teams' progress | 0,25 |  |  | Trying to connect speakers to Raspberry Pi | 3.5
|  |  | Working on the laoding sign on the app | 1 | Making intermediate poll agenda | 0.15 |  |  | Research on the speakers | 2
[5 empty] | Research on how to connect the speakers to Raspberry Pi | 3
Total |  | 5.5 |  | 6 |  | 4.15 |  | 4 |  | 6.5 |  | 2 |  | 2
Timofei Arefev
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Setting Raspberry Pi and confronting technical diffictulties | 3 | Successfully setting up raspberry pi | 3 | Research NFC | 2 | Reasearch on Bluetooth | 3 | Work on project (Atelier) | 3 | Reasearch on Bluetooth | 1 | Learn React Native | 4 | 30
|  |  | Working with NFC scaner | 3 | Work on project (Atelier) | 3 |  |  |  |  | Learn React Native | 2
|  |  | Work on project (Atelier) | 3
Total |  | 3 |  | 9 |  | 5 |  | 3 |  | 3 |  | 3 |  | 4
Daryl Genove
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier (Self-Study React Notification) | 3 | Atelier (Self Study React Map) | 3 | Atelier(Self Study React Map) | 3 | Self-Study (Map) | 6 | Atelier | 3 | Self-Study(Fixe Errors) | 3 | Self-Study(Locate Location) | 3 | 27
|  |  | Process-Professional Skills | 3
Total |  | 3 |  | 6 |  | 3 |  | 6 |  | 3 |  | 3 |  | 3
Peter Zlamala
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
0
Total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Erika Nicolau
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Setting Raspberry Pi and confronting technical diffictulties | 3 | Setting Raspberry Pi and confronting technical diffictulties | 2 | Preparing for the intermediate poll | 1.5 | Research to connect the speaker to the Raspberry Pi | 2 | Adjusting documents | 2 |  |  |  |  | 26
| Learning about how to program on the Raspberry Pi | 2 | Working with NFC scaner | 3 | Intermediate poll | 0.5 | Research how we can implement a LED for the bag | 2 | Updating the time table | 1
[5 empty] | Team meeting | 2 | Research how can we obtain a bigger range for the NFC | 3 | Trying to oder pins for the logo of the bag | 2
Total |  | 5 |  | 5 |  | 4 |  | 7 |  | 5 |  | 0 |  | 0
Jia Men Lam
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Learning how to use android studio | 3 | Implement features on the app - remove, add , rename bags / items - mobile friendly | 4 | Poll meeting | 0.5 | Working on the app: - bluetooth - GPS | 5 | Working on the app: - bluetooth - GPS | 5 | 360 feedback & communication evaluation | 2 |  |  | 26
[5 empty] | Team discussion about the product | 1
[5 empty] | Research about GPS | 2.5
[5 empty] | Working on the app design | 3
Total |  | 3 |  | 4 |  | 7 |  | 5 |  | 5 |  | 2 |  | 0

## Week 6
Time Table Date : 3 - 7 Jun
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday |  | Total / week
| 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
Mihael Druzeta
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier | 3 | Atelier | 3 | Atelier | 3 | Studying | 2 | Algorithm Programming Contest | 8 |  |  |  |  | 31
| Writing documentation | 1 | Writing documentation | 1 | Building bluetooth testing | 2
|  |  | Developing app | 2
|  |  | Hakathon | 6
Total |  | 4 |  | 12 |  | 5 |  | 2 |  | 8 |  | 0 |  | 0
Mihaela Covali
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Working on the NFC tags | 4 | Quality control documentation | 1 | Updating design documentation | 2 | Working on the Tehnical Advisory Report | 3 | Working in the Techical Advisory Report | 1.5 |  |  |  |  | 30
| Control progress on the team App | 1 | Quality control code | 1.5 | Starting the Technical Advisory Report | 2 |  |  | Quality control documentation | 2
| Updating documentation based on the team's progress | 2.5 | Revising all the documentation for the project | 2 | Quality control | 2
| Working on connecting speakers | 1 | Connecting speakers to Raspberry Pi | 2
|  |  | Burning the spekers do to high power | 0.5
|  |  | Research on what I did wrong with the speakers | 2
Total |  | 8.5 |  | 9 |  | 6 |  | 3 |  | 3.5 |  | 0 |  | 0
Timofei Arefev
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier | 3 | Hakathon | 6 | Atelier | 3 | Atelier | 3 | Research bluetooth | 2 |  |  |  |  | 28
|  |  | Atelier | 3 |  |  | Test build of a bluetooth | 3 | Algorithm contest | 5
Total |  | 3 |  | 9 |  | 3 |  | 6 |  | 7 |  | 0 |  | 0
Daryl Genove
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier (Resize Design) | 4 | Atelier | 4 | Atelier | 4 | Process (Resize Design, Apply Images) | 4 | Algorithm Contest | 8 |  |  |  |  | 28
|  |  | Fixing the applications visual | 1 | Cleaning the code | 3
Total |  | 4 |  | 5 |  | 7 |  | 4 |  | 8 |  | 0 |  | 0
Peter Zlamala
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
0
Total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Erika Nicolau
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Working on the NFC tags | 3 | Revising the code of the app | 2 | Updating design documentation | 2 | Quality control documentation | 2 | Working in the Techical Advisory Report | 3 |  |  |  |  | 34.5
| Learninng aboout connection with Raspberry Pi | 3 | Revising all the documentation for the project | 2 | Starting the Technical Advisory Report | 4 | Updating the time table | 1 | Algorithm Contest | 8
|  |  | Connecting speakers to Raspberry Pi | 2 | Quality control | 1
|  |  | Burning the spekers do to high power | 0.5
|  |  | Research on what I did wrong with the speakers | 1
Total |  | 6 |  | 7.5 |  | 7 |  | 3 |  | 11 |  | 0 |  | 0
Jia Men Lam
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Working on the app: - bluetooth - GPS | 4 | Working on the app: - bluetooth - GPS | 4.5 | Working on the app: - Merging code - fixing conflict -fixing errors | 3.5 | Working on the app: - Merging code - fixing conflict -fixing errors | 6 | Working on the app: - Merging code - fixing conflict -fixing errors | 4 |  |  |  |  | 25
[5 empty] | Checking group process | 1 |  |  | Working on the app: - bluetooth | 2
Total |  | 4 |  | 4.5 |  | 4.5 |  | 6 |  | 6 |  | 0 |  | 0

## Week 7
Time Table Date : 10 - 14 Jun
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday |  | Total / week
| 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16
Mihael Druzeta
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier | 3 | Atelier | 3 | Studying at home | 2 | Studying at home | 2 | Atelier | 3 | Studying at home | 2 | Studying at home | 2 | 20
| Moving to wifi instead of bluetooth | 1 | Process | 0.5 |  |  |  |  | Writing feedbacks to each team member | 1.5
Total |  | 4 |  | 3.5 |  | 2 |  | 2 |  | 4.5 |  | 2 |  | 2
Mihaela Covali
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Working on the bluetooth connection | 4 | Working on wifi connection | 4 | Research on how to build a 3D model | 1 | Research on wifi connection | 3 | Filing the logo so it is smooth | 1 |  |  |  |  | 21
|  |  | Going to Lionel Smith for advice | 0.5 | Building the 3D model logo | 3 |  |  | Stiching the logo to the bag | 0.5
[5 empty] | Working on wifi connection | 2 |  |  | Wrorking on wifi connection | 2
Total |  | 4 |  | 4.5 |  | 6 |  | 3 |  | 3.5 |  | 0 |  | 0
Timofei Arefev
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier | 3 | Atelier | 3 | Working on wifi connection | 3 | Working on wifi connection | 3 | Atelier | 4 | Working on wifi connection | 6 | Working on wifi connection | 6 | 28
Total |  | 3 |  | 3 |  | 3 |  | 3 |  | 4 |  | 6 |  | 6
Daryl Genove
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier | 4 | Atelier (Code Cleaning) | 4 | Install Compatible Version of React | 4 | Reinstalling Versions | 4 | Process (Reinstalling and Update Versions) | 4 |  |  |  |  | 27.5
| Fixing Errors | 3 | Process (Code Cleaning) | 0.5 |  |  |  |  | Atelier ( Reinstalling and Update Versions) | 4
Total |  | 7 |  | 4.5 |  | 4 |  | 4 |  | 8 |  | 0 |  | 0
Peter Zlamala
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
0
Total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Erika Nicolau
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Researching about implementing Bluetooth between Raspberry Pi and React Native | 4 | Learning how to implement Wifi connection | 4 | Research on how to build a 3D model | 1 | Research on wifi connection | 3 | Filing the logo so it is smooth | 1 |  |  |  |  | 20
|  |  | Team meeting | 1 | Printing the logo | 2 |  |  | Stiching the logo to the bag | 0.5
[5 empty] | Creating the digital logo | 3 |  |  | Filling in the time table | 0.5
Total |  | 4 |  | 5 |  | 6 |  | 3 |  | 2 |  | 0 |  | 0
Jia Men Lam
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Learning how to implement wifi feature | 4 | Learning how to implement wifi feature | 4 | Fixing code - remove unnecessary files | 3.5 | Fixing code - remove unnecessary files | 3.5 | Updating document - Technical Advisory | 3 |  |  |  |  | 21
|  |  | discussion with the team | 1 |  |  |  |  | Team general discussion | 2
Total |  | 4 |  | 5 |  | 3.5 |  | 3.5 |  | 5 |  | 0 |  | 0

## Week 8
Time Table Date : 17 - 21 Jun
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday |  | Total / week
| 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23
Mihael Druzeta
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier | 3 | Script writing | 1 | Voice recording for commercial | 1 | Voice recording for commercial | 1 | Presentation | 0.5 |  |  |  |  | 17.5
| Documentation | 2 | Atelier | 3 | Atelier | 3 | Atelier | 3
Total |  | 5 |  | 4 |  | 4 |  | 4 |  | 0.5 |  | 0 |  | 0
Mihaela Covali
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Checking the React code | 2 | Working on Bag Instructions Document | 2 | Working on the final presentation | 2 | Quality Control Code and Documentation | 4 | Final Presentation | 0.25 |  |  |  |  | 15.5
| Working on READ me file | 2.5 | Quality Control team work | 1
| Readjusting the Documentation | 1.75
Total |  | 6.25 |  | 3 |  | 2 |  | 4 |  | 0.25 |  | 0 |  | 0
Timofei Arefev
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Demostrating the product | 2 | Prepare presentation | 3 | Prepare presentation | 3 | Prepare presentation | 3 | [6 empty] | 13
| Prepare presentation | 2
Total |  | 4 |  | 3 |  | 3 |  | 3 |  | 0 |  | 0 |  | 0
Daryl Genove
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Atelier (Video Editing (Intro)) | 4 | Atelier (Video Editing (Short Commercial, Ending)) | 4 | Process (Video Editing (Merge Audio)) | 4 | Atelier(Video Editing (Finalize)) | 4 | Presentation | 4 |  |  |  |  | 24
[7 empty] | Process (Video Editing (Finalize)) | 4
Total |  | 4 |  | 4 |  | 4 |  | 8 |  | 4 |  | 0 |  | 0
Peter Zlamala
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
0
Total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Erika Nicolau
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Deciding on the presentation | 2 | Writing the script for the presentation | 3 | Writing the student assesments | 2 | Updating document - Technical Advisory - Searching for APA reference | 2 | [6 empty] | 16
| Quality control | 1 | Helping on the video | 2 | Helping on the video | 2 | Preparation for presentation | 1
[7 empty] | Quality control | 1
Total |  | 3 |  | 5 |  | 4 |  | 4 |  | 0 |  | 0 |  | 0
Jia Men Lam
| Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Description | Time / Hour | Total / week
| Updating document - Technical Advisory | 3 | Updating document - Technical Advisory - Update app design | 4 | Updating document - Technical Advisory - Searching for APA reference | 2 | Updating document - Technical Advisory - Searching for APA reference | 4 | Presentation | 0,5 |  |  |  |  | 20
| Team general disscusion | 1 | Preparation for presentation | 1 | Preparation for presentation | 2 | Preparation for presentation | 1
| Quality control team | 1 |  |  |  |  | Quality control team | 1
Total |  | 5 |  | 5 |  | 4 |  | 6 |  | 0 |  | 0 |  | 0

## Total Hours = 8 weeks
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Totaal
Mihael Druzeta | 27.5 | 36 | 22 | 30 | 25 | 31 | 20 | 17.5 | 209
Mihaela Covali | 28.5 | 23.5 | 25.5 | 27 | 30.15 | 30 | 21 | 15.5 | 201.15
Timofei Arefev | 18 | 19 | 21 | 23 | 30 | 28 | 28 | 13 | 180
Daryl Genove | 27.7 | 19 | 19.65 | 31.5 | 27 | 28 | 27.5 | 24 | 204.35
Peter Zlamala | 19 | 18.5 | 14 | 0 | 0 | 0 | 0 | 0 | 51.5
Erika Nicolau | 23.5 | 25.5 | 25.5 | 25 | 26 | 34.5 | 20 | 16 | 196
Jia Men Lam | 22.5 | 20 | 23 | 23 | 26 | 25 | 21 | 20 | 180.5